## Sheet1
ISSUE LOG
Project | Module | URL | Issue Type | Query | Date of logging | Issue status
Elearning | Lost Password | http://elearningm1.upskills.in/main/auth/lostPassword.php | Coding/configuration | The site is not able to send the email to get password | 2021-09-04 | Open
Elearning | Create course by faculty | http://elearningm1.upskills.in/main/create_course/add_course.php | Requirement | For course template there is no drop down list to select the template.Neither is there a maintanance for add/edit/delete of course template | 2021-09-03 | Open
Elearning | Create course by faculty | http://elearningm1.upskills.in/main/create_course/add_course.php | Requirement | There is no maintanace for add/edit/delete of course category | 2021-09-03 | Open
Elearning | Student_ Subscribing_ Course | http://elearningm1.upskills.in/main/auth/courses.php | Requirement | Once Student subscibe a course there is no option to unsubscribe it | 2021-09-03 | Open
Elearning | N/A | N/A | General-Network | Application pages are loading very slowly may be because of insufficient bandwidth | 2021-09-03 | Open
Elearning | N/A | N/A | General-Stability | Application new pages are deployed during the time of testing | 2021-09-03 | Open
Elearning | N/A | N/A | General-Data | Data unavailable for testing registration,login modulees | 2021-09-03 | Open