## Sheet1
Defect ID | TC id | TS id | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Module/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Elearning_User_Forgotpassword_TC01 | TS01 | Cycle1 | Build_ST_01 | System testing | Release | 2021-09-04 | Bindu |  |  | Elearning_Faculty_Forgot_Password |  | Forgot password not working | QA |  |  | Coding |  | Defect | Medium | New | If an user whether student or faculty forgets the password the site is not able to send the password through mail
2 | Elearning_Student/faculty_EditProfile_TC01 | TS01 | Cycle1 | Build_ST_02 | System testing | Release | 2021-09-04 | Arpita S |  |  | Elearning_Edit_profile |  | Edit profile not working | QA |  |  | Coding |  | Defect | Medium | New | There is no option to change the other fields of user's profile
3 | Elearning_Student/faculty_EditProfile_TC01 | TS01 | Cycle1 | Build_ST_03 | System testing | Release | 2021-09-05 | Arpita S |  |  | Elearning_Edit_profile |  | Edit profile not working | QA |  |  | Coding |  | Defect | High | New | User after changing password in edit profile is not updating
4 | Elearning_Student_Registration_TC01 | TS01 | Cycle1 | Build_ST_04 | System testing | Release | 2021-09-06 | Akshara |  |  | Elearning_Student_Registration |  | After registration confirmation is not done | QA |  |  | Coding |  | Defect | Medium | New | After user registering to website credentials are not sent to emailid
5 | Elearning_user_searc_courses_TC01 | TS01 | Cycle1 | Build_ST_05 | System testing | Release | 2021-09-06 | Ankita DV |  |  | Elearning_Search_Functionality |  | Search courses inappropriate functioning | QA |  |  | Design |  | Defect | Low | New | If course name is left empty,still it displays all courses available in catalog. It is desirable to have pagination in the search results to make it more user friendly
6 | Elearning_Faculty_Create_course_TC01 | TS01 | Cycle1 | Build_ST_06 | System testing | Release | 2021-09-07 | Arpitha Naik |  |  | Elearning_Faculty_Create_course |  | While creating course template is not working | QA |  |  | Design |  | Defect | Medium | New | For Faculty create course, course template there is no drop down list to select the template.
7 | Elearning_Faculty/Student_personal agenda_TC02 | TS01 | Cycle1 | Build_ST_07 | System testing | Release | 2021-09-06 | Ankita DV |  |  | Elearning_User_Personal_agenda |  | Personal agenda Name inappropriately functioning | QA |  |  | UI |  | Defect | Low | New | If name field is empty the agenda gets created
8 | Elearning_Faculty_Create_course_TC02 | TS01 | Cycle2 | Build_ST_08 | System testing | Release | 2021-09-07 | Arpitha Naik |  |  | Elearning_Faculty_Create_course |  | Category field inappropriately functioning | QA |  |  | Design |  | Defect | Medium | New | Category field should be mandatory
9 | Elearning_Faculty_Create_course_TC02 | TS01 | Cycle2 | Build_ST_09 | System testing | Release | 2021-09-08 | Arpitha Naik |  |  | Elearning_Faculty_Create_course |  | Course code field inappropriately functioning | QA |  |  | Design |  | Defect | Medium | New | Course code field should be mandatory
10 | Elearning_Student_Subscribing_course_TC01 | TS01 | Cycle2 | Build_ST_10 | System testing | Release | 2021-09-09 | Ankita DV |  |  | Elearning_Student_Subscribing_course |  | Course cant be unsubscribed | QA |  |  | Coding |  | Defect | Medium | New | Once student subscribe the course there is no option to unsubscribe it