## Sheet6
Row Labels | Count of Severity
High | 1
Low | 2
Medium | 9
Grand Total | 12

## Sheet7
Row Labels | Count of Reason Code
Coding | 5 | Coding | 5
Design | 4 | Design | 4
Requirement | 2 | Requirement | 2
UI | 1 | UI | 1
Grand Total | 12 | Grand Total | 12
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sheet9
Count of Severity | Column Labels
Row Labels | Cycle1 | Cycle2 | Grand Total
High | 1 |  | 1
Low | 2 |  | 2
Medium | 4 | 3 | 7
Grand Total | 7 | 3 | 10

## Sheet10
Count of Severity | Column Labels
Row Labels | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | Grand Total
High | [6 empty] | 1 | bar: 2021-09-05
Low | 2021-09-06: 2 | 2
Medium | 2 |  | 3 | 2 | 1 | 1 | 9
Grand Total | 2 | 1 | 5 | 2 | 1 | 1 | 12

## Sheet1
Defect ID | TC id | TS id | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Module/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Elearning_User_Forgotpassword_TC01 | TS01 | Cycle1 | Build_ST_01 | System testing | Release | 2021-09-04 | Bindu |  |  | Elearning_Faculty_Forgot_Password |  | Forgot password not working | QA |  |  | Coding |  | Defect | Medium | New | If an user whether student or faculty forgets the password the site is not able to send the password through mail
2 | Elearning_Student/faculty_EditProfile_TC01 | TS01 | Cycle1 | Build_ST_02 | System testing | Release | 2021-09-04 | Arpita S |  |  | Elearning_Edit_profile |  | Edit profile not working | QA |  |  | Coding |  | Defect | Medium | New | There is no option to change the other fields of user's profile
3 | Elearning_Student/faculty_EditProfile_TC01 | TS01 | Cycle1 | Build_ST_03 | System testing | Release | 2021-09-05 | Arpita S |  |  | Elearning_Edit_profile |  | Edit profile not working | QA |  |  | Coding |  | Defect | High | New | User after changing password in edit profile is not updating
4 | Elearning_Student_Registration_TC01 | TS01 | Cycle1 | Build_ST_04 | System testing | Release | 2021-09-06 | Akshara |  |  | Elearning_Student_Registration |  | After registration confirmation is not done | QA |  |  | Coding |  | Defect | Medium | New | After user registering to website credentials are not sent to emailid
5 | Elearning_user_searc_courses_TC01 | TS01 | Cycle1 | Build_ST_05 | System testing | Release | 2021-09-06 | Ankita DV |  |  | Elearning_Search_Functionality |  | Search courses inappropriate functioning | QA |  |  | Design |  | Defect | Low | New | If course name is left empty,still it displays all courses available in catalog. It is desirable to have pagination in the search results to make it more user friendly
6 | Elearning_Faculty_Create_course_TC01 | TS01 | Cycle1 | Build_ST_06 | System testing | Release | 2021-09-07 | Arpitha Naik |  |  | Elearning_Faculty_Create_course |  | While creating course template is not working | QA |  |  | Design |  | Defect | Medium | New | For Faculty create course, course template there is no drop down list to select the template.
7 | Elearning_Faculty/Student_personal agenda_TC02 | TS01 | Cycle1 | Build_ST_07 | System testing | Release | 2021-09-06 | Ankita DV |  |  | Elearning_User_Personal_agenda |  | Personal agenda Name inappropriately functioning | QA |  |  | UI |  | Defect | Low | New | If name field is empty the agenda gets created
8 | Elearning_Faculty | NA | Cycle1 | Build_ST_08 | System testing | Release | 2021-09-06 | Arpitha Naik |  |  | Elearning_faculty |  | There is no interface for adding/editing/deleting course template | QA |  |  | Requirement |  | Defect | Medium | New | Requirement for course template maintenance is missing. During course addition the course template can be selected from list rather then text box
9 | Elearning_Faculty | NA | Cycle1 | Build_ST_09 | System testing | Release | 2021-09-06 | Arpitha Naik |  |  | Elearning_faculty |  | There is no interface for adding/editing/deleting course category | QA |  |  | Requirement |  | Defect | Medium | New | Requirement for course category maintenance is missing. During course addition the course category can be selected from list rather then text box
10 | Elearning_Faculty_Create_course_TC04 | TS01 | Cycle2 | Build_ST_10 | System testing | Release | 2021-09-07 | Arpitha Naik |  |  | Elearning_Faculty_Create_course |  | Category field inappropriately functioning | QA |  |  | Design |  | Defect | Medium | New | Category field should be mandatory
11 | Elearning_Faculty_Create_course_TC03 | TS01 | Cycle2 | Build_ST_11 | System testing | Release | 2021-09-08 | Arpitha Naik |  |  | Elearning_Faculty_Create_course |  | Course code field inappropriately functioning | QA |  |  | Design |  | Defect | Medium | New | Course code field should be mandatory
12 | Elearning_Student_Subscribing_course_TC01 | TS01 | Cycle2 | Build_ST_12 | System testing | Release | 2021-09-09 | Ankita DV |  |  | Elearning_Student_Subscribing_course |  | Course cant be unsubscribed | QA |  |  | Coding |  | Defect | Medium | New | Once student subscribe the course there is no option to unsubscribe it